## Sheet1
S.No | Date | Reported By | Project | Environment | Title | Module | Sub Module | Priority | Steps | Actual Result | Expected Result
1 | 2019-01-26 | Masrath sultana | Charleston | Dev | Site Operation History UI is not proper | Sites | View Sites | 3 | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Sites->View Sites, select any site and click on View History button. | UI for Site Operation History Grid is not proper | Grid should be aligned properly.
2 | 2019-01-26 | Masrath sultana | Charleston | Dev | Not able to view comments for adult surveillance in Site Operation History grid | Sites | View Sites | 2 | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Do adult surveillance for any Site from site annotation and add comments 4. Navigate to Sites->View Sites, select site and click on View History button and view the comments column. | Comments column not getting updated | Should view the adult Trap surveillance comments in Site Operation History grid.
3 | 2019-01-26 | Masrath sultana | Charleston | Dev | Site Visit data not getting updating in Action History | Sites | View Sites | 2 | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Sites->View Sites, select any site and click on Map Selected. 4. Click on Site Visit and enter all data and click on Save Changes. 5. Click on Action History in Annotation box | Unable to view Site Visit in Action History. | Should view the Site Visit in Action History
4 | 2019-01-26 | Masrath sultana | Charleston | Dev | Unable to download Job and Shape File | Sites | View Sites |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Sites->View Sites, select any site and click on Map Selected. 4. Click on Block and draw block on field map and click on Create .shape/.Job file | Should download job and shape file | Unable to download shape and job file
5 | 2019-01-26 | Masrath sultana | Charleston | Dev | Unable to uplaod file in Site Update page | Sites | View Sites |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Sites->View Sites, select any site and upload file(png) in Site Update page. | File should be updated successfully | Unable to update file
6 | 2019-01-26 | Masrath sultana | Charleston | Dev | Save Changes button not working in Site Property Add | Master Management | Site Property |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Master Management->Site Property, click on Add and enter Property name and click on Save Changes | Save Changes button click is not working | Should save Site Property and view in Site Property grid.
7 | 2019-01-26 | Masrath sultana | Charleston | Dev | Getting Merced address signature in Send Direction email. | Sites | View Sites |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Sites->View Sites, select any site and click on Send Direction | Signature in the Email should be Charleston | Signature is merced in email.
8 | 2019-01-26 | Masrath sultana | Charleston | Dev | Showing wrong status in PDF download of Activity Card for Approved | Activity Card | View Activity Card |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Activity Card-> View Activity Card and click on PDF download and view the status of Approved in PDF | Status should be approved in PDF. | Status is as Open in PDF download for approved Activity ID.
9 | 2019-01-26 | Masrath sultana | Charleston | Dev | Getting unnecessary popup on clicking Create Workflow | Map | Field Map |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Map->Field Map, Click on create Workflow | Should open popup to enter workflow details | Getting unnecessary popup on clicking Create Workflow
10 | 2019-01-26 | Masrath sultana | Charleston | Dev | Unable to delete workflow | Sites | View Sites |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Sites->Workflow, Click on delete for any workflow. | Should delete workflow and not be able to view in the grid | Unable to delete workflow
11 | 2019-01-26 | Masrath sultana | Charleston | Dev | Workflow getting created after clicking Cancel button | Map | Field Map |  | 1. Launch URL:https://charleston.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Map->Field Map, Click on create Workflow and link sites to work flow and click on Cancel. | Workflow should not be created | Able to create workflow after clicking cancel button also.