## Sheet1
Date | Reported By | Project | D_ID | Priority | Environment | Module | Sub Module | Title | Execution steps | Expected Result | Actual Result
2018-11-21 | Masrath Sultana | Antelope | D_001 |  | DEV | Master Management | Actions |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Master Management-> Actions. 4. Click on CSV download button | Data should be same as displaced in the grid. | One row data in CSV is not proper. | No issue now
2018-11-21 | Masrath Sultana | Antelope | D_002 |  | DEV | Master Management | Announcements |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Master Management->Announcements. 4.Add announcement with long text and click on CSV download | Data should be same as displaced in the grid. | Data is not displaying proper if text is so long in description. | No issue now
2018-11-21 | Masrath Sultana | Antelope | D_003 |  | DEV | Master Management | Larval Breeding List |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Master Management->Larval Breeding List. 4. Delete any item in the list. 5. Naviagte to Site-> View Site, and select any site and click on Map Selected and in Activities click on Larval Surveillance. 6. Click on Breeding dropdown. | Should not view deleted items in breeding dropdown | Able to view items in breeding dropdown that are deleted. | No issue now
2018-11-21 | Masrath Sultana | Antelope | D_004 |  | DEV | Master Management | Site Type |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Master Management->Site Type.(view the subtypes) 4. Navigate to Reports-> Adult Count Report and Trap Type by Genus. | Able to view extra sub type items which are not in list. | Should view only sub types which are present in Master Management. | No issue now
2018-11-21 | Masrath Sultana | Antelope | D_005 |  | DEV | Master Management | SR Status |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Master Management->SR Status.(View status) 4. Navigate to Service Request-> Service Request, click on any SR and view the status dropdown | Should have Open status in dropdown as it is present in master management | No open status.
2018-11-21 | Masrath Sultana | Antelope | D_006 |  | DEV | Service Request | Service Requests |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request-> Service Requests. 4. Click on Add in SR page, and view the status | Status must be New | Status is Open.
2018-11-23 | Masrath Sultana | Antelope | D_007 |  | DEV | Service Request | View Public Page |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->View Public Page. 4. Click on "To Submit Service request Click Here". 5. Check Mosquito check box and enter all the Questions and click save. 6. Navigate to Pending public Queue and click on SR and convert to internal SR. | Gate code field is becoming NULL | Should display value what we have given on public page.
2018-11-23 | Masrath Sultana | Antelope | D_008 |  | DEV | Service Request | View Public Page |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->View Public Page. 4. Click on "To Submit Service request Click Here". 5. Check Mosquito check box and view the Questions. 6. View SR label Mosquito Questions from SR page, View from Pending public Queue. | Mandatory Questions astrick(*) must be same for same page. | Mandatory Questions astrick(*) is changing for same page.
2018-11-23 | Masrath Sultana | Antelope | D_009 |  | DEV | Service Request | Pending Public Queue |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->Pending Public Queue. 4. Edit any SR. | Should display Questions matching Antelopevalley | Displaying many questions for SR type Mosquito
2018-11-23 | Masrath Sultana | Antelope | D_010 |  | DEV | Service Request | Pending Public Queue |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->Pending Public Queue. 4. Select Pending SR and click on Convert to internal SR. 5. Change the address from map. Note: Same issue from Service Request page-> ADD. | Should display country name | Country is becoming empty.
2018-11-23 | Masrath Sultana | Antelope | D_011 |  | DEV | Service Request | Service Requests |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Raise a SR from View Public page, Convert to Internal SR and view Site column from the grid. | Should have site details | Site details showing empty after raising SR from Public page
2018-11-23 | Masrath Sultana | Antelope | D_12 |  | DEV | Service Request | Service Requests |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->Service Requests. 4. Edit any SR having New Status | Status must be new in SR form. | Status is New in grid on editting the same SR status is Open
2018-11-23 | Masrath Sultana | Antelope | D_13 |  | DEV | Service Request | Service Requests |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->Service Requests. 4. click on Open hyperlink | Should dsipaly SRs having status Open | Displaying Srs having New status.
2018-11-23 | Masrath Sultana | Antelope | D_14 |  | DEV | Dashbaord | Service Requests |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. View the dashboard SR ID 5, status is Review. 4. SR ID 5 in Service Request Status is cancelled | Status must be same in dashbaord and SR page | Mismatch of status between SR page and Dashbaord.
2018-11-23 | Masrath Sultana | Antelope | D_15 |  | DEV | Service Request | Service Requests |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Service Request->Service Requests. 4. Select any open SR and navigate to maps, In Larvel Survillance enter Reinspection date. | Status of SR must be changed to Reinspect | Status is not getting changed.
2018-11-23 | Masrath Sultana | Antelope | D_16 |  | DEV | Surveillance | Adult Surveillance |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Surveillance-> Adult Surveillance/traps, and click on PDF/CSV download. | In Grid it is displaying Trap Collected date but in PDF/CSV it is displaying trap counted date. | In Grid it is displaying Trap Collected date
2018-11-26 | Masrath Sultana | Antelope | D_17 |  | DEV | Activity Card | View Activity Card |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Activity Card-> View Activity Card. | Should have Approve button. | Approve button missing. | 1484
2018-11-26 | Masrath Sultana | Antelope | D_18 |  | DEV | Activity Card | View Activity Card |  | 1. Launch URL:https://merced.dev.leateamapps.com/ 2. Enter User name and password. 3. Navigate to Activity Card-> View Activity Card. | Should not have Deparment Column | Dept column is not used in the form.
| masrath Sultana | Antelope |  |  | dev | Sites | View Site Block | Sites-View Site Block-Area not populating for block created from Shape File from Opeation Plan Map | Steps to Reproduce: 1. Launch URL: https://sangabrielvalley.test.leateamapps.com 2. Enter User name and password. 3. Navigate to Map-Operation Plan-Blocks-Import from shape file, choose shape file and click on Process File->Finish, in Block Add popup enter details and click on save changes. 4. Navigate to Sites-View Site Block, view the added block from shape file. | Should view the area of block | Area of block is missing for block added from shape file.